## Notes
Use the cloud adoption plan | Cloud adoption plan for the deployment to Azure DevOps - Cloud Adoption Framework ¦ Microsoft Docs
The cloud adoption plan organizes activities by activity type:
Epics: An epic represents an overall phase of the cloud adoption lifecycle.
Features: Features are used to organize specific objectives within each phase. For instance, migration of a specific workload is a feature.
User stories: User stories group work into logical collections of activities based on a specific goal.
Tasks: Tasks are the actual work to be done.
At each layer, activities are sequenced based on dependencies. Activities are linked to articles in the Cloud Adoption Framework to clarify the objective or task at hand.
The clearest view of the cloud adoption plan comes from the Epics backlog view. For help with the backlog view, see view a backlog. From the backlog view, it's easy to plan and manage the work required to complete the current phase of the adoption lifecycle.
Note: The current state of the cloud adoption plan focuses heavily on migration efforts. Tasks related to governance, innovation, or operations must be populated manually.
Align the cloud adoption plan
The overview pages for the Strategy methodology and the Plan methodology refer to the strategy and plan template. The template organizes the decisions and data points. The data points align the template for the cloud adoption plan with your specific plans for adoption. Consider completing the exercises in the Strategy methodology and the Plan methodology before your new project begins.
The following articles support alignment of the cloud adoption plan:
Workloads: To capture workloads that might be migrated or modernized, align features within the cloud migration epic. Add and modify those features to migrate your top 10 workloads.
Assets: Each asset (virtual machine, application, or data) is represented by the user stories under each workload. Add and modify those user stories to align with your digital estate.
Rationalization: As each workload is defined, the initial assumptions about that workload can be challenged. The workload might result in changes to the tasks under each asset.
Create release plans: Iteration paths establish release plans by aligning efforts with various releases and iterations.
Establish timelines: To define the start and end dates for each iteration, create a timeline to manage the overall project.
These five articles help with the alignment tasks required to start managing your adoption efforts. The next step gets you started on the alignment exercise.

## Cloud Adoption Plan
ID | Work Item Type | Title 1 | Title 2 | Title 3 | Title 4 | Assigned To | State | Tags
1 | Epic | Cloud Adoption Strategy |  |  |  |  | New | Strategy
11 | Feature |  | Define Adoption Strategy |  |  |  | New | Strategy
90 | User Story |  |  | Motivations |  |  | New | Strategy
91 | User Story |  |  | Business Outcomes |  |  | New | Strategy
92 | User Story |  |  | Business Case |  |  | New | Strategy
93 | User Story |  |  | First Adoption Project |  |  | New | Strategy
2 | Epic | Cloud Adoption Plan |  |  |  |  | New | Plan
10 | Feature |  | Define the Cloud Adoption Plan |  |  |  | New | Plan
86 | User Story |  |  | Digital Estate |  |  | New | Plan
87 | User Story |  |  | Initial organizational alignment |  |  | New | Plan
88 | User Story |  |  | Skills readiness plan |  |  | New | Plan
89 | User Story |  |  | Update this Cloud Adoption Plan |  |  | New | Plan
12 | Task |  |  |  | Prioritize workloads |  | New | Plan
13 | Task |  |  |  | Align assets to workloads |  | New | Plan
14 | Task |  |  |  | Define iterations and releases |  | New | Plan
15 | Task |  |  |  | Create timelines |  | New | Plan
3 | Epic | Cloud Ready |  |  |  |  | New | Ready
9 | Feature |  | Landing zone creation |  |  |  | New | Ready
82 | User Story |  |  | Azure Readiness Guide |  |  | New | Ready
84 | User Story |  |  | Landing zone considerations |  |  | New | Ready
85 | User Story |  |  | Deploy the landing zone |  |  | New | Ready
4 | Epic | Cloud Innovation |  |  |  |  | New | Innovation
5 | Epic | Cloud Migration |  |  |  |  | New | Migration
6 | Feature |  | First Workload |  |  |  | New | First Workload
22 | Task |  |  | Azure Migration Guide |  |  | New | First Workload
34 | Task |  |  | Select the first workload |  |  | New | First Workload
45 | Task |  |  | Review Expanded Scope Checklist |  |  | New | First Workload
54 | Task |  |  | Review Best Practices |  |  | New | First Workload
63 | Task |  |  | Update the adoption plan |  |  | New | First Workload
7 | Feature |  | First Host |  |  |  | New | First Host
79 | User Story |  |  | Extend the landing zone for VMWare |  |  | New | First Host
28 | Task |  |  |  | Escalate private cloud privileges |  | New | First Host
29 | Task |  |  |  | Configure on-premises DNS for private cloud |  | New | First Host
67 | Task |  |  |  | Configure workload DNS and DHCP setup |  | New | First Host
80 | User Story |  |  | Migrate VMs |  |  | New | First Host
26 | Task |  |  |  | Prerequisites |  | New | First Host
30 | Task |  |  |  | Migrate ISOs and Templates |  | New | First Host
49 | Task |  |  |  | Migrate VMs using PowerCLI |  | New | First Host
50 | Task |  |  |  | Migrate VMs using NSX Layer 2 VPN |  | New | First Host
69 | Task |  |  |  | Migrate VMs using backup and disaster recovery tools |  | New | First Host
81 | User Story |  |  | Update migration assessment, decision tree, and tooling |  |  | New | First Host
27 | Task |  |  |  | Evaluate migration options used to migrate the first host |  | New | First Host
68 | Task |  |  |  | Update the migration tooling decision tree to reflect VMWare migration options |  | New | First Host
8 | Feature |  | Workload Template |  |  |  | New | Workload Template
70 | User Story |  |  | Prerequisites |  |  | New | Workload Template
19 | Task |  |  |  | Decisions |  | New | Workload Template
37 | Task |  |  |  | Roles and Responsibilities |  | New | Workload Template
57 | Task |  |  |  | Environment readiness (Landing Zone) |  | New | Workload Template
71 | User Story |  |  | Assess the workload |  |  | New | Workload Template
23 | Task |  |  |  | Evaluate workload and asset readiness |  | New | Workload Template
33 | Task |  |  |  | Architect workload |  | New | Workload Template
46 | Task |  |  |  | Estimate Cloud Costs |  | New | Workload Template
53 | Task |  |  |  | Migration tool choice(s) |  | New | Workload Template
64 | Task |  |  |  | Change approval process |  | New | Workload Template
72 | User Story |  |  | VM - UX Server |  |  | New | Workload Template
18 | Task |  |  |  | Assess |  | New | Workload Template
38 | Task |  |  |  | Migrate |  | New | Workload Template
43 | Task |  |  |  | Optimize workload(s) |  | New | Workload Template
56 | Task |  |  |  | Secure and Manage |  | New | Workload Template
59 | Task |  |  |  | Document configuration |  | New | Workload Template
73 | User Story |  |  | VM - Middle Tier |  |  | New | Workload Template
25 | Task |  |  |  | Assess |  | New | Workload Template
31 | Task |  |  |  | Migrate |  | New | Workload Template
48 | Task |  |  |  | Optimize workload(s) |  | New | Workload Template
51 | Task |  |  |  | Secure and Manage |  | New | Workload Template
66 | Task |  |  |  | Document configuration |  | New | Workload Template
74 | User Story |  |  | VM 3 - SQL Server |  |  | New | Workload Template
24 | Task |  |  |  | Assess |  | New | Workload Template
32 | Task |  |  |  | Migrate |  | New | Workload Template
47 | Task |  |  |  | Optimize workload(s) |  | New | Workload Template
52 | Task |  |  |  | Secure and Manage |  | New | Workload Template
65 | Task |  |  |  | Document configuration |  | New | Workload Template
75 | User Story |  |  | Test Workload |  |  | New | Workload Template
17 | Task |  |  |  | Set up Azure Monitor to track performance |  | New | Workload Template
39 | Task |  |  |  | Manual test with power users |  | New | Workload Template
42 | Task |  |  |  | Create/select automated test |  | New | Workload Template
60 | Task |  |  |  | Scale Test |  | New | Workload Template
76 | User Story |  |  | Optimize Workload Assets |  |  | New | Workload Template
16 | Task |  |  |  | Review test results |  | New | Workload Template
40 | Task |  |  |  | Decide on optimization timing |  | New | Workload Template
41 | Task |  |  |  | Adjust sizing |  | New | Workload Template
61 | Task |  |  |  | Document change |  | New | Workload Template
77 | User Story |  |  | Promote Workload |  |  | New | Workload Template
21 | Task |  |  |  | Network dependencies |  | New | Workload Template
35 | Task |  |  |  | Security Review |  | New | Workload Template
44 | Task |  |  |  | Governance Review |  | New | Workload Template
55 | Task |  |  |  | Final test |  | New | Workload Template
62 | Task |  |  |  | Promotion |  | New | Workload Template
78 | User Story |  |  | Decomission Retired Assets |  |  | New | Workload Template
20 | Task |  |  |  | Power down assets |  | New | Workload Template
36 | Task |  |  |  | Workload monitoring period |  | New | Workload Template
58 | Task |  |  |  | Decommission |  | New | Workload Template